## Developer To-Do
AMZ Visuals - Developer To-Do (Relaunch)
Live tool >> old prototype. Backend = Supabase, /designer route exists. Relaunch = fix + finish. Work top-down. Source = Loom timestamp / video frame. Fill Effort/Owner/Status yourself.
ID | Priority | Topic | Type | Task | Information | Source | Sprint | Effort | Owner | Status
B1 | Blocker | Onboarding | Bug | Signup broken / no confirmation email | New users cannot register; no confirmation email (not in spam). Check Supabase Auth + SMTP/email provider (templates, sender domain, rate limits). Test full signup with a fresh email. Add proper error/success states. | 02:24-03:37 | 1 |  |  | Open
B2 | Blocker | Payments | Bug | Checkout does not complete (stays 'pending') | UI shows 'payment successful' but order stays 'payment pending'; even with a 100% code. Verify Stripe webhook (checkout.session.completed / payment_intent.succeeded) is received and sets order status. Handle the 100%-discount (0 EUR) path separately. Fix the long 'finish order' loading. | 13:00-15:14 | 1 |  |  | Open
B3 | Blocker | AI Module | Bug | AI image generation not running | AI generation does not start at all. Check AI provider connection/keys/quota; log errors. Restore flow: product -> type 'Main Image' -> reference image -> generate. | 23:30 | 1 |  |  | Open
H1 | High | Order Flow | Bug | State loss on tab switch | While creating a product/order, switching browser tab (to copy a competitor ASIN) sometimes logs the user out / loses progress. Autosave the product + order draft. | 11:32-12:19 | 2 |  |  | Open
H2 | High | Order Status | Bug | Wrong status 'in progress' after approve-anyway | After 'approve anyway', the status must be 'finalizing', not 'in progress'. | 17:36 | 2 |  |  | Open
H3 | High | Designer | Bug | Designer dashboard does not auto-update | Designer must reload to see new state. Add live / auto refresh. | 18:24 | 2 |  |  | Open
H4 | High | Designer | Adjustment | Approval state misleading for designer | With 'approve anyway' (no per-item approval) the designer sees 'approved' although items are not approved and user comments exist. Make the real review status unambiguous; surface user comments prominently. | 19:20 | 2 |  |  | Open
H5 | High | Notifications | New | No completion notification / email | On 'mark complete' the client gets no in-app notification and no email. Notification must also be set to unread; send the client an email. | 21:43 | 2 |  |  | Open
U1 | Medium | Copy | Adjustment | Fix 'few projects' text | After payment it says 'few projects' -> should read 'View project' / 'View visual order'. | 14:11 | 2 |  |  | Open
U2 | Medium | Review UI | Adjustment | Order overview has too much copy | Overview is text-heavy; the key info is hard to see. Simplify, sharpen the hierarchy. | 15:56 | 2 |  |  | Open
U3 | Medium | Review UI | Adjustment | 'Pending review' once per product, not per image | Show 'Pending review' once next to the product name (e.g. 'Main V1 - Pending review'), not on every image. | 16:13 | 2 |  |  | Open
U4 | Medium | Review UI | Adjustment | Approved image clearly shows 'Approved' | After approving a single image it must clearly show 'Approved'; the approve button then disappears for it. | 17:15 | 3 |  |  | Open
U5 | Medium | Order Flow | Adjustment | Consider removing 'Review order' step | The separate 'Review order' step seems unnecessary -> consider going straight to payment. | 12:39 | 3 |  |  | Open
U6 | Medium | Review UI | Adjustment | Remove 'Feedback' wording for client | On a finished project, remove anything labeled 'Feedback' for the client; replace with 'Not happy? Reach out to us' + contact email. | 22:07 | 2 |  |  | Open
U7 | Medium | Download | Adjustment | Improve download discoverability | From a finished order the download is hard to find. Add a clear hint/link: 'To download -> Visual Library'. | 22:21 | 3 |  |  | Open
U8 | Low | Brand Form | Adjustment | Hint: brand guide replaces colors/fonts | Add a hint in the brand form: 'If a brand guide is uploaded, colors/fonts are optional.' | 05:13 | 5 |  |  | Open
V1 | Low | Copy | Bug | Typo 'No Gas' -> 'No-Gos' | Brand form shows 'No Gas'; should be 'No-Gos'. | Frame f9 | 2 |  |  | Open
V2 | Medium | UI/Design | Adjustment | Raise global text contrast | Info banners, helper texts and placeholders are light-gray on light; landing subheadline / CVR lines are barely readable. Raise contrast to WCAG AA. | Frames f1,f7,f9,f19,f46 | 2 |  |  | Open
V3 | Medium | UI/Design | Bug | Chat widget overlaps CTAs / modals | The 'Got any questions?' chat overlaps the primary CTA (e.g. 'Create Brand') and the upload modal. Fix position / z-index. | Frames f7,f9,f52 | 2 |  |  | Open
V4 | Medium | Stability | Bug | Empty / broken render states | Several fully blank app screens (Supabase URLs visible) during the flow. Add loading / error states. Related to B1/B2/B3. | Frames f3,f50,f54 | 2 |  |  | Open
A2 | High | AI Module | New | AI prompt agent for main image | From product data + uploaded image, auto-build a strong main-image concept: combine a relevant element (e.g. product + chicken), suggest a badge/hook (e.g. '40% Protein'), make food look more appetizing where it makes sense. Target: click-through-strong Amazon main images. | 24:39-26:03 | 3 |  |  | Open
A3 | High | AI Module | New | Product fidelity (compositing / inpainting) | Preserve the real product from the photo; only generate scene/background. No pure text-to-image (it would alter the product -> unusable for Amazon). | spec | 3 |  |  | Open
A4 | Medium | AI Module | New | Text via overlays / templates | Render badge / infographic text as editable overlay layers, not via AI (legibility). | spec | 3 |  |  | Open
A5 | Medium | AI Module | New | Amazon conformity guardrail | Validate dimensions, white background for hero, no invalid claims/badges before download. | spec | 3 |  |  | Open
A6 | Medium | AI Module | Architecture | ImageProvider abstraction | Wrap the image model behind an ImageProvider interface; models change often. | spec | 3 |  |  | Open
AV1 | Medium | Ad-Video | New | Ad-video stage 1 (template / motion) | Template/motion-based video (images + animation + text + music, e.g. Remotion) + render worker. Export presets: Amazon Listing / Sponsored Brands / 9:16 / 1:1. Buyable in-tool (subscription/credits). | spec | 4 |  |  | Open
AV2 | Low | Ad-Video | New | Ad-video stage 2 (generative) | Generative AI video behind a VideoProvider interface (Kling/Runway/Veo) as a premium add-on, later. | spec | later |  |  | Open
P1 | High | Partner Program | New | Connect Tolt to Stripe | Set up Tolt on Stripe: tracking links, cookie attribution, partner dashboards, 25% lifetime commission, payouts via Wise/Payoneer/PayPal. Tolt reads the real Stripe charges, so lifetime + net-of-discount is handled natively. | decision 13.06 | 4 |  |  | Open
P2 | High | Partner Program | New | Agency attribution at signup | Store ?ref=CODE from the affiliate link in a cookie and attach it to the user at signup (referred_by_agency). Add an optional signup field 'Referred by an agency? (name/code)' as a fallback. | decision 13.06 | 4 |  |  | Open
P3 | Medium | Partner Program | New | Partner dashboard (lean) | Read-only view for agencies: referred clients, revenue, commission earned, payout status. v1 can come from Tolt; native later. | decision 13.06 | 4 |  |  | Open
P6 | Medium | Partner Program | New | Agency-managed mode (optional) | For agencies ordering in their own account for clients: 25% standing discount instead of commission; clients as brands. Uses existing structures. | decision 13.06 | later |  |  | Open
S1 | High | Subscriptions | New | Stripe subscription + Customer Portal | New monthly recurring plans parallel to one-time services (e.g. 'Ad Premium Package' = 5 brand ad creatives + 3 ad videos/month). Stripe Product + recurring monthly Price, Checkout in subscription mode. Enable Stripe Customer Portal for self-serve cancel (at period end), card update, invoices = near-zero dev. | decision 13.06 | 4 |  |  | Open
S2 | High | Subscriptions | New | Plan/quota data model (generic, multi-tier) | Data-driven plans with monthly quotas JSON e.g. {ad_creative:5, ad_video:3}; subscriptions + per-period quota_usage tables tied to org_id. Build GENERIC (multiple tiers planned), not hardcoded to one package. | decision 13.06 | 4 |  |  | Open
S3 | High | Subscriptions | New | Subscription webhooks | Handle checkout.session.completed/subscription.created (provision + set first-period quota), invoice.paid (RESET monthly quota = new period), subscription.updated (status, cancel_at_period_end, plan change), subscription.deleted, invoice.payment_failed (past_due + restrict). Verify signatures, idempotent. | decision 13.06 | 4 |  |  | Open
S4 | High | Subscriptions | New | Quota enforcement (use-it-or-lose-it) | On each ad-creative/ad-video generation: if period used_count < limit -> allow + increment atomically, else BLOCK with reset date. No rollover, no overage (block until next cycle). | decision 13.06 | 4 |  |  | Open
S5 | Medium | Subscriptions | New | Plans UI + usage display | New Plans/Subscription section (tier cards), Subscribe CTA. Current plan with remaining-this-month (e.g. 'Creatives 3/5, Videos 2/3'), renews date, Manage/Cancel -> Customer Portal. Disable generate + show reset date when exhausted; past_due banner. | decision 13.06 | 4 |  |  | Open
S6 | Low | Subscriptions | New | Upgrade/downgrade handling | Mid-cycle plan change: Stripe handles billing proration; quota change applies from next period (v1). Refine later. | decision 13.06 | later |  |  | Open
ARCH1 | High | Architecture | Architecture | Multi-tenancy / org_id from day 1 | Introduce org_id / tenant_id in the data model, auth & storage now (even if full white-label comes later). Retrofitting is expensive. | handoff | 1 |  |  | Open
ARCH2 | Medium | Architecture | Architecture | Async jobs / queue | Run AI generation & video rendering via a queue + status + webhooks; never synchronously inside the request. | handoff | 3 |  |  | Open
ARCH3 | Low | Architecture | Architecture | Logging / monitoring | Ensure logging/monitoring so failures are visible ('a lot of things have been downed'). | - | 1 |  |  | Open

## Context & Architecture
Context & Architecture
Topic | Note
Key fact | The live deployed tool is far more built than the old prototype (sb1-oc1x2hve). Signup, payment, designer dashboard with versioning, visual library and an AI module already exist. The 3 priorities = FIX + FINISH, not greenfield.
Stack (live) | Backend = Supabase (*.supabase.co URLs visible in frames). Own /designer route. For B1/B2 check Supabase Auth/RLS/webhooks/keys and the Stripe webhook first.
Multi-tenancy | Add org_id/tenant_id from day 1 (data model, auth, storage) - even though full white-label is later. Retrofitting is expensive.
AI provider abstraction | Wrap image/video models behind ImageProvider / VideoProvider interfaces; models change monthly.
Async | AI generation & video rendering run via queue + status + webhooks, never synchronously.
Partner program | Affiliate model (not white-label). Tool = Tolt on Stripe. Commission = 25% lifetime on the actual paid amount. Minimal custom dev = ref-cookie capture + optional signup agency field.
Suggested sprints | Sprint 1: prerequisites + blockers (B1,B2,B3) + ARCH1/ARCH3 -> relaunch-ready. Sprint 2: high bugs (H1-H5) + main UX/visual (U1,U2,U3,U6,V1,V2,V3,V4). Sprint 3: finalize AI module. Sprint 4: partner program (Tolt) + ad-video stage 1. Remaining UX ongoing.
Full docs | Repo JonasK01/amzvisualsai, branch claude/hopeful-gauss-41dvp7: docs/01-10. Narrative dev brief = docs/10-developer-todo.md.